## Summary
Backend Security Audit — Findings Register
Source | backend-security-audit canvas · reviewed 2026-08-29
Severity | Count
Critical | 4
High | 8
Medium | 12
Low | 4
Total | 28
Columns
ID | Finding identifier (C=Critical, H=High, M=Medium, L=Low)
Severity | Priority for remediation
Theme | Category (auth, LLM cost, perf, etc.)
Finding | Technical one-line summary from the audit
Location | Primary file(s) in backend/app
Description | Plain-language explanation of the issue and how to fix it

## Backend Findings
ID | Severity | Theme | Finding | Location | Description (issue + how to solve)
C1 | Critical | DoS / cost | CaptureRequest.content and raw_html have no max_length — JWT holders can POST multi-MB bodies that hit Storage + pipeline + Haiku | schemas/sources.py:35-36 | When someone captures a page or transcript, the API currently accepts content of any size. A logged-in user (or stolen JWT) can send multi-megabyte payloads. That bloats storage and then forces the AI pipeline to process everything — which is expensive and can slow or crash the server. How to solve: Add max_length limits in the Pydantic schema (e.g. ~500k chars for content, ~2M for raw_html). Also set a max request body size at the server and file-size limits on the Supabase storage bucket.
C2 | Critical | Abuse | No app-level rate limits on login, capture, chat, coverage, or rebuild (RateLimitError only wraps HF 429) | errors.py, routers/* | There is no throttle on how often someone can try passwords, capture sources, ask chat questions, or regenerate coverage. Attackers can brute-force logins or burn AI budget by calling expensive endpoints repeatedly. The existing RateLimitError only passes through Hugging Face rate limits — the app itself does not limit users. How to solve: Add rate limiting (e.g. SlowAPI or Redis token bucket). Suggested starting points: ~5 login attempts per 15 minutes per IP; ~20 chat turns per minute per user; ~10 captures per minute; ~1 coverage regen per space per hour.
C3 | Critical | LLM cost | Lazy GET /summary runs two separate Haiku calls and races the pipeline — up to 4× spend; no credit charge | source_chat_service.py:64-66 | Opening a source summary can trigger two separate AI calls (plain summary + structured summary). The background pipeline may also be generating a summary at the same time. If the user opens the page early, you can pay up to four times for the same document, and no credits are charged for this path. How to solve: Reuse the pipeline's single map-reduce bundle (summarize_document_bundle). Skip generation on GET while processing_status is still in-flight. Add a per-source lock so concurrent requests do not duplicate work. Optionally meter this path or only generate in the pipeline.
C4 | Critical | Auth / CORS | cors_allow_any_extension defaults True with credentials — misconfigured prod reflects any chrome-extension:// origin | config.py:58, main.py:34-37 | By default the API allows requests from any Chrome extension origin with credentials. Production can turn this off via env, but if that env var is missing, every extension can talk to the API. That widens who can send Authorization headers from an extension page. How to solve: Change the default to False. In production, refuse to start if the flag is True or if allowed web origins are empty. Only pin known extension IDs in CORS_EXTENSION_ORIGINS.
H1 | High | Data integrity | URL-less PDFs hash to sha256('') — later upload upserts and overwrites the earlier row | capture_service.py:84-91, 251 | PDF uploads without a URL all get the same content hash (hash of an empty string). Because captures are idempotent on (space_id, content_hash), a second PDF in the same space can overwrite the first one's database row. How to solve: Hash from a client-provided file digest, or use a unique nonce / actual file bytes hash — never fall back to hashing an empty string for PDFs.
H2 | High | Bug | POST /sources/upload-url never enqueues pipeline.run — PDFs stay queued with no chunk/embed/summarize | routers/sources.py:67-73 | Normal captures start the AI pipeline after save. PDF upload-url only mints a signed upload URL and creates a row — it never starts chunking, embedding, or summarizing. PDFs can sit forever in 'queued'. How to solve: Add a complete-upload (or webhook) endpoint that runs after the client finishes the PUT, then enqueue pipeline.run the same way POST /sources does.
H3 | High | LLM cost | Coverage, graph rebuild, and lazy summary are unmetered LLM spend (only capture + ask credits exist) | coverage_service.py, concept_service.py, credits_service.py | Credits only cover new captures and chat asks. Regenerating coverage, rebuilding the knowledge graph, and lazy summary generation can call Anthropic for free. Users (or scripts) can burn AI budget without depleting their credit balance. How to solve: Meter these endpoints with credits, or hard-throttle them (rate limits + caches). Prefer generating coverage/summary in the capture pipeline and make GET read-only from cache.
H4 | High | Billing race | consume_ask is TOCTOU: ensure + set_ask_units is non-atomic (unlike consume_credits RPC) | credits_service.py:80-107 | Ask credits work like '3 questions = 1 credit'. The code reads the counter, then writes it back in two steps. Two chat requests at the same time can both see the same count and under-charge the user. How to solve: Make ask_units updates atomic in Postgres (same pattern as the consume_credits RPC) — a single SQL function that increments and consumes under a row lock.
H5 | High | LLM cost | Chat history is unbounded; empty RAG falls back to up to 40k extract inside the system prompt | source_chat_service.py:128-137, 171-172 | Every chat turn sends the entire past conversation to the model. If retrieval finds no chunks, it dumps up to 40,000 characters of the source into the system prompt. Long threads get very expensive, and putting page text in the system prompt also raises prompt-injection risk. How to solve: Keep only the last ~8 turns (or a token budget). Prefer retrieved chunks only; do not fall back to the full extract in the system prompt. Put document text in a user/document turn instead.
H6 | High | Authz / cost | GET /summary uses require_viewable_source — collaborators can trigger free Haiku regeneration | source_chat_service.py:50-66 | Collaborators are allowed to view a source summary (good). But if the summary is missing, their GET regenerates it with Haiku at no credit cost. Shared readers can unintentionally (or intentionally) spend the owner's AI budget. How to solve: Only owners (or the pipeline) generate summaries. Collaborators should get a cached summary or a 'still processing' response — never trigger a paid LLM call.
H7 | High | Auth / perf | JWT verified via remote auth.get_user every request + fresh Supabase client — latency and Auth SPOF | dependencies.py:161-172 | Every authenticated API call asks Supabase Auth over the network to validate the JWT, and builds a new client each time. That adds ~50–200ms latency and means if Auth is down, the whole API is down. How to solve: Verify JWTs locally with Supabase's JWKS / JWT secret. Reuse a shared auth client. Keep remote get_user only for sensitive account operations if needed.
H8 | High | Authz depth | Service-role bypasses RLS; save_summary / list_messages / list_unextracted filter only by source_id | space_repo.py | The backend uses the Supabase service-role key, which bypasses row-level security. Some repository methods filter only by source_id, not user_id. Callers usually check ownership first — but one missed check becomes a cross-tenant bug. How to solve: Keep ownership checks in services, and add user_id (or space ownership) filters in the repository methods as defense in depth. Audit every write that keys only on source_id.
M1 | Medium | API | CORS allow_methods is GET/POST/OPTIONS — PUT/PATCH/DELETE preflight fails for direct browser clients | main.py:28 | The API only allows GET, POST, and OPTIONS in CORS. Real features use PUT/PATCH/DELETE (notes, folders, profile). The Next.js BFF hides this for the web app, but a browser or unpacked extension talking to the API directly will fail preflight. How to solve: Add PUT, PATCH, and DELETE to allow_methods if any browser client must call the backend directly. Or document that only the BFF may use mutating verbs.
M2 | Medium | Prompt inj. | Captured page text is interpolated into CHAT_SYSTEM_PROMPT (highest-trust slot) | llm_service.py:50-62 | Chat builds a system prompt that includes the captured page title, summary, and extract. System prompts are the highest-trust instructions. A malicious or jokey web page that says 'ignore previous instructions' sits in that trusted slot. How to solve: Keep a short, static system prompt. Put untrusted document text in a separate user or document message so the model treats it as data, not instructions.
M3 | Medium | Storage | Signed PUT URLs have no app-enforced size or post-upload MIME verification | storage_repo.py, note_service.py | Clients upload PDFs and note images via signed URLs. The app does not enforce a max file size or verify the real file type after upload. Someone could upload a huge blob or a non-image file labeled as PNG. How to solve: Set bucket file-size limits in Supabase. After upload, verify Content-Type / magic bytes before linking the object to a note or source.
M4 | Medium | Bug | Graph rebuild marks failed sources extracted so unextractable PDFs never retry | concept_service.py:164-170 | When graph rebuild fails on a source (common for PDFs with no text), it marks that source as 'concepts extracted' so the loop can finish. Those sources never get another chance to join the knowledge map. How to solve: Use a distinct failure status (or retry count) instead of marking done. Skip permanently unextractable sources without pretending they succeeded.
M5 | Medium | LLM / race | GET /coverage is a write with no lock — concurrent cache misses stampede syllabus regen | coverage_service.py:38-74 | Loading coverage can trigger an AI syllabus generation and then cache it. If several tabs or spaces refresh at once on a cache miss, each one pays for a full Haiku call. How to solve: Generate coverage in the pipeline or via an explicit POST. Make GET cache-only. Add a lock or debounce so only one regen runs per space at a time.
M6 | Medium | Perf | CoverageService / PlanService call require_owned_space sync inside async handlers | coverage_service.py:39, plan_service.py | Most services offload sync Supabase calls with anyio.to_thread so they do not block the async event loop. Coverage and plan still call require_owned_space inline, which can stall other requests under load. How to solve: Wrap those sync ownership checks in anyio.to_thread.run_sync, matching CaptureService and SourceChatService.
M7 | Medium | API | OpenAPI /docs /redoc left on by FastAPI defaults; GET /auth/me returns raw profile dict | main.py, routers/auth.py:44-50 | FastAPI's interactive docs (/docs, /redoc) are publicly enabled by default, which helps attackers map the API. /auth/me also returns a raw profile dict, so any extra DB columns could leak to the client. How to solve: Disable docs in production (docs_url=None). Return a typed Pydantic response model for /auth/me with only the fields the UI needs.
M8 | Medium | Reliability | Pipeline is FastAPI BackgroundTasks: lost on restart, no retry, no concurrency cap | routers/sources.py:60-63 | After capture, AI work runs as an in-process background task on the web server. If the process restarts, jobs are lost. There is no retry and no limit on how many pipelines run at once, so load can stall the API. How to solve: Move the pipeline to a real queue/worker (Render worker, pgmq, Inngest, etc.). Cap in-flight jobs per user and retry failed stages.
M9 | Medium | Privacy | Invite-by-username returns distinct 404 copy — username enumeration | sharing_service.py | Inviting a collaborator returns a message that effectively reveals whether a username exists ('No Atlas user'). Attackers can probe for valid usernames. How to solve: Use the same generic error for missing, private, and invalid usernames (e.g. 'Unable to invite that user').
M10 | Medium | LLM cost | Concept vocabulary concatenated unbounded into system prompt; map stages run sequentially | llm_service.py:281-320 | When extracting concepts, the whole space vocabulary is stuffed into the system prompt. Large spaces waste tokens. Map windows also run one after another, which is slow and holds workers longer. How to solve: Send only the top-N nearest existing labels (or a char-capped list). Parallelize map-stage LLM calls carefully with a concurrency limit.
M11 | Medium | Logging | X-Request-Id is echoed from the client (correlation spoofing / log injection) | logging.py:58-59 | If a client sends X-Request-Id, the server reuses it in logs and the response. Attackers can inject fake IDs to confuse log correlation or pollute log aggregators. How to solve: Always generate a server-side request ID (or validate/sanitize client IDs to a safe UUID format). Optionally keep a separate client_request_id field.
M12 | Medium | Perf | Sharing N+1 profile fetches; folder listing loads sources to count; no Anthropic usage logging | sharing_service.py, llm_service.py | Listing collaborators or 'shared with me' loads each profile in a separate query (N+1). Folder counts may load many source rows just to tally. Anthropic token usage is not logged, so you cannot see where money goes. How to solve: Batch-fetch profiles in one query. Use SQL counts for folders. Log input/output tokens (and cache hits) from Anthropic responses for cost observability.
L1 | Low | Auth | Login password min_length=1; unused UserSignup allows min_length=6 | schemas/auth.py:23-35 | Login accepts passwords as short as one character. Signup schema allows six characters but is unused (signup happens via Supabase/frontend). Weak passwords are easier to guess if login is not rate-limited. How to solve: Align password policy with Supabase (e.g. min 8+). Keep rate limits on login (see C2).
L2 | Low | DoS | UpdateNotePageRequest.content is unbounded TipTap JSON | schemas/notes.py:73 | Note updates accept any size TipTap JSON document. A huge note can bloat the database and slow reads/writes. How to solve: Cap serialized content size (e.g. max JSON bytes or node count) in the schema or service layer.
L3 | Low | Hygiene | Public profile and top reviews have no scrape throttle | routers/profile.py, routers/reviews.py | Public endpoints for profiles and top reviews can be scraped at unlimited speed. Low severity alone, but easy to abuse for enumeration or scraping. How to solve: Add IP-based rate limits on public GETs (even generous ones).
L4 | Low | Auth | Login response includes refresh_token — XSS on any caller that stores the body steals the session | auth_service.py:50 | The backend login response includes a refresh_token in JSON. Any frontend that stores that body (or any XSS that can read it) can steal a long-lived session. Prefer putting session material only in httpOnly cookies on the BFF. How to solve: Avoid returning refresh tokens to browser JS. Have the BFF set httpOnly cookies and return only a redirect / status. Align with the frontend audit (stop echoing tokens from /api/auth/login).